## Daily Report
[23 empty] | RPT DATE: |  |  | 2021-01-05
[24 empty] | RPT NUM: |  | 2
[23 empty] | RIG: |  |  | Frontier Rig 16
WELL/JOB INFORMATION
WELL NAME: |  |  | FORGE 16A [78]-32 | [10 empty] | JOB: |  | DFIT
FIELD: |  |  | 0 | [10 empty] | LEASE: |  | 0
AFE #: |  |  | 0 | [10 empty] | API #: |  | 0
CONTRACTOR: |  |  | Frontier Drilling | [10 empty] | SUPERVISOR: |  | D Winkler, L Swearingen, V Welch
TD: |  |  |  | 10987 |  |  | TMD |  | 8559 |  |  | TVD |  | RIG PHONE: |  | 0
PBTD: |  |  |  | 0 |  |  | TMD |  | 0 |  |  | TVD |  | EMAIL: |  | 0
Present Ops: |  |  | TRIP IN HOLE WITH 3 1/2 DRILL PIPE | [25 empty] | TRIP IN HOLE WITH 3 1/2 DRILL PIPE
Next 24 Hours: |  |  | DRILL OUT CMT, FLOATS AND CIRCULATE OUT SAND | [25 empty] | DRILL OUT CMT, FLOATS AND CIRCULATE OUT SAND
COST SUMMARY
COMPLETION AFE AMT: |  |  |  | 0 |  |  |  |  | DAILY COMP COST: |  |  |  |  | 52569 |  |  |  | CUM COMP COST: |  |  |  |  | 52569
TIME LOG
From | To |  | Hrs |  | Phase |  |  |  | Activity |  |  |  | NPT Code |  |  | Operations
6:00 | 20:00 |  | 14 |  | Well Prep |  |  |  | Pressure Test BOPs |  |  |  | 0 |  |  | Weld on wellhead as per API specs Nipple up and test BOPE; Annular 250 psi low / 5,000 psi high Blind rams, pipe rams, choke lines, manifold, floor valves, top drive valves 250 psi low / 10,000 psi high Casing 1,500 psi Accumulator function test | [11 empty] | Weld on wellhead as per API specs Nipple up and test BOPE; Annular 250 psi low / 5,000 psi high Blind rams, pipe rams, choke lines, manifold, floor valves, top drive valves 250 psi low / 10,000 psi high Casing 1,500 psi Accumulator function test
20:00 | 6:00 |  | 10 |  | Well Prep |  |  |  | Trips |  |  |  | 0 |  |  | Make up BHA and pick up 3 1/2" drill pipe to 7,300' | [11 empty] | Make up BHA and pick up 3 1/2" drill pipe to 7,300'
0:00 | 0:00 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0 | [11 empty] | 0
0:00 | 0:00 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0 | [11 empty] | 0
0:00 | 0:00 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0 | [11 empty] | 0
0:00 | 0:00 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0 | [11 empty] | 0
0:00 | 0:00 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0 | [11 empty] | 0
0:00 | 0:00 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0 | [11 empty] | 0
0:00 | 0:00 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0 | [11 empty] | 0
0:00 | 0:00 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0 | [11 empty] | 0
0:00 | 0:00 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0 | [11 empty] | 0
0:00 | 0:00 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0 | [11 empty] | 0
0:00 | 0:00 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0 | [11 empty] | 0
0:00 | 0:00 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0 | [11 empty] | 0
0:00 | 0:00 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0 | [11 empty] | 0
0:00 | 0:00 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0 | [11 empty] | 0
0:00 | 0:00 |  | 0 |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  | 0 | [11 empty] | 0
Total Hours |  |  | 24
FLUID DATA
Fluid Type |  |  |  |  | Mud | [7 empty] | Weight |  |  |  | 9
Fluid Loss Day |  |  |  |  | 0 | [7 empty] | Fluid Loss Cum |  |  |  | 0
CONSUMABLES
Type |  |  | Daily Rec'd |  |  |  |  | Daily Used |  |  |  |  | Daily Net |  |  |  | Cum Rec'd |  |  |  | Cum Used |  |  |  | Amount on Hand
Fuel |  |  | 0 |  |  |  |  | 1811 |  |  |  |  | -1811 |  |  |  | 13360 |  |  |  | 3137 |  |  |  | 10223
Drill Water |  |  | 314 |  |  |  |  | 0 |  |  |  |  | 314 |  |  |  | 314 |  |  |  | 0 |  |  |  | 314
0 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
0 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
SAFETY
Safety Meeting Topic | [5 empty] | NIPPLE UP / NIPPLE DOWN BOP STACK
Last BOP Test | [5 empty] | 2021-01-05 | [6 empty] | BOP Test Due |  |  |  | 2021-02-05 |  |  |  |  | Accidents |  |  | 0
CASING
Type | [6 empty] | OD |  | ID |  | Weight |  |  | Grade |  | Bottom MD |  |  | Connection |  |  | Remarks
Conductor | [6 empty] | 20 |  | 19 |  | 54 |  |  | A53B |  | 130 |  |  | Welded |  |  | 0
Surface | [6 empty] | 13.375 |  | 12.41 |  | 68 |  |  | L-80 |  | 1629 |  |  | BTC |  |  | 0
Intermediate | [6 empty] | 9.625 |  | 8.75 |  | 40 |  |  | HCL-80 |  | 5110 |  |  | BTC |  |  | 0
Production | [6 empty] | 7 |  | 5.92 |  | 38 |  |  | T-95 |  | 10787 |  |  | JFELION |  |  | 0
0 | [6 empty] | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  |  | 0
0 | [6 empty] | 0 |  | 0 |  | 0 |  |  | 0 |  | 0 |  |  | 0 |  |  | 0
PERFORATIONS
Stage |  | Top MD |  |  | Bottom MD |  |  | Density |  | EHD |  | Phasing |  |  | Stage |  | Top MD |  |  | Bottom MD |  |  | Density |  | EHD |  | Phasing
FRAC
Stage |  | Pump Time |  |  | Avg Rt / PSI |  |  |  |  | Max Rt / PSI |  |  |  |  | Stage |  | Pump Time |  |  | Avg Rt / PSI |  |  |  |  | Max Rt / PSI
0 |  | 0 | [12 empty] | 0 |  | 0
0 |  | 0 | [12 empty] | 0 |  | 0
0 |  | 0 | [12 empty] | 0 |  | 0
0 |  | 0 | [12 empty] | 0 |  | 0
www.wellez.com WellEz On Demand ver_01.04.21gw

## Data (hidden)
WELL INFO |  |  |  | JOB INFO |  |  |  |  | DAILY OPS Values | [9 empty] | Cum | [5 empty] | CONSUMABLES | [5 empty] | BOP |  | TUBING | [7 empty] | WFE - Casing -Summary Information - Static | [15 empty] | ACTIVITY TIMES | [6 empty] | Completion Intangible |  |  | Completion Tangible |  |  |  |  | PERFORATIONS | [15 empty] | Frac Sum - C#10
Well | Field | Lease | API # | Contractor | Rig | Comp AFE # | Comp AFE $ | Job Name | Date | Report # | Supervisor | PBTD TD | PBTD TVD | Present Operations | Activity Planned | Safety Meeting Topic | Rig Phone | Accidents | Type | Weight | Viscosity | Formation Loss Daily | Formation Loss |  | Drill Water | [5 empty] | Last BOP Test | BOP Test Due | Type | OD | ID | Weight | Grade | Btm Pipe MD | Length | Remarks | [15 empty] | C#1 | Start Time | End Time | Duration | Description | Phase | Activity | NPT Code | [8 empty] | 0 | Stage | Top TD | Btm TD | Shot Density | EHD | Phasing | Perforation Date | [7 empty] | Count | CPL #1 | C#27 | C#6 | C#8 |  | C#7 | C#9
[24 empty] | Type | Daily Received | Daily Used | Daily Net | Cum Rec'd | Cum Used | Amt on Hand | [10 empty] | Casing Type | Casing ID | OD | ID | Weight | Grade | Connection | Length | TMD | TVD | Top of Cement | Date Csg Run | Time Csg Run | Date Csg Pulled | Time Csg Pulled | Remarks | [7 empty] | Code | Daily | Cum | Code | Daily | Cum | Daily | Cum | Records |  |  |  |  | Hole Size |  |  | Count | Perf Zone | Top MD | Bottom MD | Density | EHD | Phasing | Records | Stage # | Pump Time | AVG Slurry Rate | Max Slurry Rate | Concatenate | AVG Treat PSI | Max Treat PSI | Concatenate | Stage | Pump Time | AVG Concat | Max Concat
FORGE 16A [78]-32 |  |  |  | Frontier Drilling | Frontier Rig 16 |  |  | DFIT | 44201 | 2 | D Winkler, L Swearingen, V Welch | 0 | 0 | TRIP IN HOLE WITH 3 1/2 DRILL PIPE | DRILL OUT CMT, FLOATS AND CIRCULATE OUT SAND | NIPPLE UP / NIPPLE DOWN BOP STACK | 0 | 0 | Mud | 9 | 55 | 0 | 0 | Fuel |  | 1811 | -1811 | 13360 | 3137 | 10223 | 44201 | 44232 |  | 3.500 | 2.764 | 13.3 | S-135 |  |  |  | Conductor | 4 | 20 | 19 | 54 | A53B | Welded | 130 | 130 | 130 | 0 | 2020-10-30 |  |  |  |  | 6:00 | 20:00 | 14 | Weld on wellhead as per API specs Nipple up and test BOPE; Annular 250 psi low / 5,000 psi high Blind rams, pipe rams, choke lines, manifold, floor valves, top drive valves 250 psi low / 10,000 psi high Casing 1,500 psi Accumulator function test | Well Prep | Pressure Test BOPs |  | -200 | 0 | 0 | -300 | 0 | 0 | 52569 | 52569 | 0 | [14 empty] | 0 | [8 empty] | 0 | 0
[24 empty] | Drill Water | 314 | 0 | 314 | 314 | 0 | 314 | [10 empty] | Surface | 1 | 13.375 | 12.41 | 68 | L-80 | BTC | 1631.09 | 1629 | 1629 | 0 | 44135 |  |  |  |  | 20:00 | 6:00 | 10 | Make up BHA and pick up 3 1/2" drill pipe to 7,300' | Well Prep | Trips |  | -201 | 0 | 0 | -301 | 0 | 0 |  |  | 0 | [23 empty] | 0 | 0
[9 empty] | TMD | TVD | DO Active | Email | [28 empty] | Intermediate | 5 | 9.625 | 8.75 | 40 | HCL-80 | BTC | 5110 | 5110 | 5109.18 | 0 | 44146 | [11 empty] | -202 | 38000 | 38000 | -302 | 0 | 0 |  |  | 0 | [23 empty] | 0 | 0
[9 empty] | 10987 | 8559 | 1 | 0 | [28 empty] | Production | 6 | 7 | 5.92 | 38 | T-95 | JFELION | 10769.92 | 10787 | 0 |  | 44197 | [11 empty] | -203 | 1104 | 1104 | -303 | 0 | 0 |  |  | 0 | [23 empty] | 0 | 0
[64 empty] | -204 | 1100 | 1100 | -304 | 0 | 0 |  |  | 0 | [23 empty] | 0 | 0
[64 empty] | -205 | 500 | 500 | -305 | 0 | 0 |  |  | 0 | [23 empty] | 0 | 0
[9 empty] | DAILY OPS 1 | [54 empty] | -206 | 60 | 60 | -306 | 0 | 0 |  |  | 0 | [23 empty] | 0 | 0
[9 empty] | Date | Report # | Supervisor | PBTD TD | PBTD TVD | Present Operations | Activity Planned | Safety Meeting Topic | Rig Phone | Accidents | [45 empty] | -207 | 60 | 60 | -307 | 0 | 0 |  |  | 0 | [23 empty] | 0 | 0
[64 empty] | -208 | 0 | 0 | -308 | 0 | 0 |  |  | 0
[9 empty] | 44201 | 2 | D Winkler, L Swearingen, V Welch |  |  | TRIP IN HOLE WITH 3 1/2 DRILL PIPE | DRILL OUT CMT, FLOATS AND CIRCULATE OUT SAND | NIPPLE UP / NIPPLE DOWN BOP STACK | [47 empty] | -209 | 0 | 0 | -309 | 0 | 0 |  |  | 0
[64 empty] | -210 | 0 | 0 | -310 | 0 | 0 |  |  | 0
[9 empty] | TMD | TVD | Email | [52 empty] | -210B | 120 | 120 | -311 | 0 | 0 |  |  | 0
[9 empty] | 10987 | 8559 | [53 empty] | -211 | 0 | 0 | -312 | 0 | 0 |  |  | 0
[64 empty] | -212 | 0 | 0 | -311 | 0 | 0 |  |  | 0
[64 empty] | -213 | 5000 | 5000 | -312 | 0 | 0 |  |  | 0
[9 empty] | DAILY OPS 2 | [54 empty] | -214 | 0 | 0 | [5 empty] | 0
[9 empty] | Date | Report # | Supervisor | PBTD TD | PBTD TVD | Present Operations | Activity Planned | Safety Meeting Topic | Rig Phone | Accidents | [45 empty] | -215 | 0 | 0 | [5 empty] | 0
[64 empty] | -216 | 0 | 0 | [5 empty] | 0
[64 empty] | -217 | 0 | 0 | [5 empty] | 0
[64 empty] | -218 | 0 | 0 | [5 empty] | 0
[9 empty] | TMD | TVD | Email | [52 empty] | -219 | 0 | 0 | [5 empty] | 0
[64 empty] | -220 | 0 | 0 | [5 empty] | 0
[64 empty] | -221 | 3185 | 3185 | [5 empty] | 0
[64 empty] | -221 | 0 | 0 | [5 empty] | 0
[9 empty] | DAILY OPS 3 | [54 empty] | -222 | 0 | 0 | [5 empty] | 0
[9 empty] | Date | Report # | Supervisor | PBTD TD | PBTD TVD | Present Operations | Activity Planned | Safety Meeting Topic | Rig Phone | Accidents | [45 empty] | -223 | 0 | 0 | [5 empty] | 0
[64 empty] | -224 | 0 | 0 | [5 empty] | 0
[64 empty] | -225A | 0 | 0 | [5 empty] | 0
[64 empty] | -225 | 0 | 0 | [5 empty] | 0
[9 empty] | TMD | TVD | Email | [52 empty] | -226 | 600 | 600 | [5 empty] | 0
[64 empty] | -227 | 0 | 0 | [5 empty] | 0
[64 empty] | -228 | 0 | 0 | [5 empty] | 0
[64 empty] | -229 | 0 | 0 | [5 empty] | 0
[64 empty] | -230 | 0 | 0 | [5 empty] | 0
[64 empty] | -232 | 0 | 0 | [5 empty] | 0
[64 empty] | -231 | 0 | 0 | [5 empty] | 0
[64 empty] | -232 | 0 | 0 | [5 empty] | 0
[64 empty] | -XX | 0 | 0 | [5 empty] | 0
[64 empty] | -233 | 0 | 0 | [5 empty] | 0
[64 empty] | -235A | 0 | 0 | [5 empty] | 0
[64 empty] | -234 | 0 | 0 | [5 empty] | 0
[64 empty] | -235 | 0 | 0 | [5 empty] | 0
[64 empty] | -238 | 0 | 0 | [5 empty] | 0
[64 empty] | -237 | 0 | 0 | [5 empty] | 0
[64 empty] | -238 | 0 | 0 | [5 empty] | 0
[64 empty] | -239 | 0 | 0 | [5 empty] | 0
[64 empty] | -242 | 0 | 0 | [5 empty] | 0
[64 empty] | -243 | 0 | 0 | [5 empty] | 0
[64 empty] | -271 | 0 | 0 | [5 empty] | 0
[64 empty] | -272 | 0 | 0 | [5 empty] | 0
[64 empty] | -273 | 2840 | 2840 | [5 empty] | 0
[64 empty] | -274 | 0 | 0 | [5 empty] | 0
[64 empty] | -275 | 0 | 0 | [5 empty] | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## WellEz Log (hidden)
Date | Name | Comment / Change | Requested By
2015-03-06 | Barrett Fontenot | Update Logo for WFE Standard | Internal
2015-04-14 | Barrett Fontenot | Corrected linking for Casing section | Internal
2017-05-10 | Michael Martin | Updated for new Standard Style Guide | Internal
2017-05-17 | Michael Martin | Update for Daily Ops 1,2,3 | Internal
2018-11-06 | Stephany Acosta | updated consumables from IFE to WFE | Internal
2019-03-25 | Travis Wingerson | Updated 2019 standard: added Frac stages, plus Phase, Activity, and NPT to time log section | Internal
2019-08-06 | Michael Stoklosa | Updated to reflect WFE perf logic | Internal
2019-12-03 | Travis Wingerson | Updated WFE perf logic to prevent duplicate entries from showing up | Internal
2020-02-24 | Travis Wingerson | Updated for standard WFE Perf Fields | Internal
2020-03-25 | Travis Wingerson | Left Justify all text, center justify all numbers / dates for 2020 standard | Internal
2020-01-04 | Garrett Warren | Reformatted report number to general instead of a date | Duane Winkler